## Sheet1
Main topic | Sub topic | Type | Question | Correct Answer | Distractor 1 | Distractor 2 | Distractor 3 | References
| Comparing product adaptation in an Iterative versus flow-based environment | Apply | You are working in a team which has two cadences, one for setting up meeting and another for retrospective each week. What factor makes the team work in a flow-based environment rather than an iterative environment? | Planning work on different days and restrospective on the same day of each week. | Planning work and restrospective on the same day of each week. | Planning work at the beginning of the iteration and restrospective at the end of the iteration. | Planning work in the middle of the iteration and restrospective at the end of the iteration. | https://learning.oreilly.com/library/view/create-your-successful/9781680502947/f_0012.xhtml
|  | Analyze | You are working on a personal project and you want to see where the work starts, where it waits, how long it waits, and if there are any cycles. Which work environment cannot help you achieving these requirements? | Iterative | Flow-based | Kanban | Six-sigma | https://learning.oreilly.com/library/view/create-your-successful/9781680502947/f_0012.xhtml
| Using sustainable approaches to product adaptation | Remember | What is the other name of the term "sustainable pace" in agile methodology? | 40 hour week | 30 hour week | 72 hour week | 45 hour week | https://www.agilealliance.org/glossary/sustainable/#q=~(infinite~false~filters~(postType~(~'page~'post~'aa_book~'aa_event_session~'aa_experience_report~'aa_glossary~'aa_research_paper~'aa_video)~tags~(~'sustainable*20pace))~searchTerm~'~sort~false~sortDirection~'asc~page~1)
|  | Understand | What is true about sustainable pace in product adaptation? | The team should establish a velocity which can be sustained within normal working hours. | Working long hours is the only way to deliver on time. | A 40 hour week is only for the weaker members of the team. Others can do more. | If the team members work long hours regularly they will get used to it, and be able to sustain it. | https://www.certifytoinspire.com/wp-content/uploads/2013/01/Sample-Questions-with-Answers-for-Web-Revised-Jan-2013-v0-3.pdf
|  | Apply | Your team has been assigned a new product to be built under Agile principles. As a project manager what can you do to maintain sustainable development of the product? | Making sure all stakeholders are in pace with the speed of the project. | Making sure all stakeholders are able to absorb the deliverables from the project without requiring their participation. | Put stress on the team members if the deadline is approaching even if their creativity and alertness suffers. | During the whole project’s execution keep the effort on all stakeholders as constant as possible. | https://technology.amis.nl/2008/10/03/agile-software-development-the-principles-principle-8-agile-processes-promote-sustainable-development-the-sponsors-developers-and-users-should-be-able-to-maintain-a-constant-pace-indefinitely/
|  | Analyze | You are recruiting people for an Agile team to be deployed on a new product. Once the team is ready, what will be your expectations as per the Agile approach to team-working? | The team should strive for a sustainable pace and a normal working week | The team should expect to work longer hours towards the end of the sprint (timebox), in order to deliver all that was committed to | The team should plan to work a small amount of overtime regularly throughout the project. | The team should not “burn out” if they have to work overtime for more than eight sprints (timeboxes, iterations) in a row. | https://www.certifytoinspire.com/wp-content/uploads/2013/01/Sample-Questions-with-Answers-for-Web-Revised-Jan-2013-v0-3.pdf
| Understanding planning in an agile environment | Remember | What is the smallest unit of an Agile planning? | Story | Sprint | Milestone | Release | https://pm.stackexchange.com/questions/22510/sprint-vs-milestone-vs-release
|  | Understand | What is the approach to planning once a project is underway? | It is normal to need to plan and re-plan as the project progresses. | Plans should never be changed | Plans should only be changed with full approval of all stakeholders | Plans are not required as Agile is incremental. | https://www.certifytoinspire.com/wp-content/uploads/2013/01/Sample-Questions-with-Answers-for-Web-Revised-Jan-2013-v0-3.pdf
|  | Apply | You are a project manager of an Agile team and needs a plan for the execution of the product. What is the Agile approach to planning? | Planning should involve the whole team, not just you (Project Manager). | Planning should all be done by you (Project Manager). | Planning is not part of an Agile approach, because Agile is exploratory. | Planning should be done in detail at the outset of a project and not revisited. | https://www.certifytoinspire.com/wp-content/uploads/2013/01/Sample-Questions-with-Answers-for-Web-Revised-Jan-2013-v0-3.pdf
|  | Analyze | Given below are few of the various steps involved in a release planning process: 1. Add more iterations 2. Add stories to the iteration 3. List the stories and epics for the release 4. Discuss the details involved in each feature What should be the last step among these four steps? | Add more iterations | Add stories to the iteration | List the stories and epics for the release | Discuss the details involved in each feature | https://monday.com/blog/agile-planning/
| Estimating using affinity estimation | Remember | Who are the participants of agile affinity estimation? | Product owner of a project, scrum master to facilitate and delivery agile team. | Scrum master to facilitate and delivery agile team | Scrum master to facilitate and product owner of a project | Only delivery agile team | https://www.greycampus.com/opencampus/agile-certified-practitioner/affinity-estimation
|  | Understand | What is not a characteristic of agile affinity estimation? | Making decision within the reach of few. | Making decision fairly transparent and visible | Creating a positive and collaborative experience. | Creating a quick and easy process. | https://www.greycampus.com/opencampus/agile-certified-practitioner/affinity-estimation
|  | Apply | There are seven team members working at a billable rate of $500/day. It is estimated that the project will need 20 iterations to complete with 10 days per iteration. What is the cost of the project? | 700000 | 5000 | 35000 | 14000 | https://www.greycampus.com/opencampus/agile-certified-practitioner/affinity-estimation
|  | Analyze | Given below are the steps involved in affinity estimation: 1. Editing the wall 2. Silent Relative Sizing 3. Product owner challenge 4. Placing items into relative sizing buckets Which of the following is the initial step to proceed with estimation? | Silent Relative Sizing | Editing the wall | Product owner challenge | Placing items into relative sizing buckets | https://www.greycampus.com/opencampus/agile-certified-practitioner/affinity-estimation
| Estimating using planning poker | Remember | On which technique does the planning poker estimation is based upon? | Wideband Delphi | The Wisdom of Crowds | Dumb agent theory | Bandwagon effect | https://www.greycampus.com/opencampus/agile-certified-practitioner/planning-poker
|  | Understand | What is the role of a product owner in planning poker? | A product owner provides a short overview of one user story to be estimated. | A product owner doesn't play, chairs the meeting. | A product owner records the summary of the discussion. | A product owner lays a card face down representing their estimate for the story. | https://en.wikipedia.org/wiki/Planning_poker#Procedure
|  | Apply | You as a team-member is involved in the planning poker to create estimate for the stories. You observed that the given task is too large equivalent to a theme or feature-level story. Which card will you choose? | 20 | 8 | 100 | 13 | https://www.knowledgehut.com/tutorials/scrum-tutorial/planning-poker
|  | Analyze | There are five team members whose story points after planning poker are listed below: Member 1: 1 Member 2: 2 Member 3: 1 Member 4: 13 Member 5: 3 Which individual can be given a soap box to offer their justification for their estimate? | Member 4 | Member 2 | Member 5 | Both member 1 and 3 | https://en.wikipedia.org/wiki/Planning_poker#Procedure
| Estimating work at different granularities | Remember | Which of the following has the smallest granularity as compared with others? | Timebox | Release | Product | Portfolio | http://itsadeliverything.com/agile-project-planning
|  | Understand | What should developers do, when estimating is done for a project? | Be fully involved in the estimating process. | Be in total control of the estimating process. | Be consulted after the Team Leader (Scrum Master) has made the estimates for the team’s work. | Not make estimates unless velocity is already known. | https://www.certifytoinspire.com/wp-content/uploads/2013/01/Sample-Questions-with-Answers-for-Web-Revised-Jan-2013-v0-3.pdf
|  | Apply | You have been tasked to deliver a mobile feature which helps users to acknowledge if their mobile battery is less than 20%. Which of the following is relatively a more suitable way of breaking down this task into a more granular one? | Sprint 1: Deliver a text feature which provides percentage of battery Sprint 2: Deliver an icon feature which changes color from green to red at 20% | Sprint 1: Design an icon feature which changes color from green to red at 20%. Sprint 2: Test and deliver the icon feature. | Single sprint: Deliver a text feature which provides percentage of battery. | Single sprint: Deliver an icon feature which changes color from green to red at 20%
Analyze
| Communicating project status using a release burn up and release burn down charts | Remember
Understand
Apply
Analyze
| Communicating project status using cumulative flow diagrams | Remember
Understand
Apply
Analyze
| Managing process adaptation | Remember
Understand
Apply
Analyze
| Analyzing which types of environments lend themselves to which types of processes | Remember
Understand
Apply
Analyze
| Managing project adaptation | Remember
Understand
Apply
Analyze